HOW TO ORGANIZE A FURNITURE DRIVE

Thank you for your interest in sponsoring a Furniture Drive in your area to benefit Furniture Sharehouse.  Furniture Drives are a great way for us to collect much-needed inventory without expensive pick-up costs.  Below is an outline of what it takes to organize a furniture drive.  The actual preparation is straightforward, but the key to a successful furniture drive is PUBLICITY, so allow six weeks for planning and publicity.

DRIVE PREPARATION/PUBLICITY

- Select Drive Leader(s)

- Select Drive Date and Time (in consultation with Furniture Sharehouse)

- Select Drive Location and obtain all necessary permits/approvals

- Create Publicity Materials (FS will provide drafts - need approval before distribution):

Drive Flyer

Newsletter “blurb”

Press Release or press story

- Publicize the Drive

Municipal Website, other communications

Print Media

Local TV/Cable/Radio

On-Line Media

School District/PTA Community Newsletters

Houses of Worship Bulletins

Community Bulletin Boards (library, coffee shop, deli etc.)

Find Locations for Display Banners (provided by Furniture Sharehouse)

- Set Volunteer Shifts and sign up Volunteers

a.	Volunteer Duties: 	greet donors and help them to complete donation form

assist unloading furniture from vehicles

label multi-piece items

assist loading furniture on to truck

assist unloading truck at warehouse

- Volunteer Shifts:

Typical Drive is 9:00 to 1:00 (rain or shine)

Three Shifts 	8:30 – 11:30 (at drive site)

11:30 – 1:30 (at drive site)

1:30 to 3:30 (at warehouse to help unload)

c.	Number of Volunteers Recommended:  8 per shift

- Make arrangements for disposal of unwanted items if possible (on-site dumpster, local DPW, etc.) or resolve to turn away unwanted items (we will not take away items we can’t use).

- Walk the site with Furniture Sharehouse representative 2-3 weeks before Drive to determine truck and tent placement, traffic flow, etc.

- Solicit donations or assign responsibility for refreshments for drive volunteers (e.g., coffee and donuts for first shift, pizza for second shift)

DAY OF DRIVE

- FS will provide at least one experienced volunteer at the drive to help with set-up and to train volunteers

- Set Up Required:  	Tent (provided by FS)

Two 6’ tables (FS can supply if needed)

Six folding chairs (FS can supply if needed)

1-2 garbage cans

Sawhorses, traffic cones for delineating drop-off area

Place signs (provided by FS)

Supply Bin (pens, clipboards, tool kit etc.) provided by FS

Refreshments, Beverage Coolers

- Furniture Sharehouse truck will arrive on-site 45 mins. before Drive Time with 1-2 professionals who will stay throughout and pack the truck

- At end of Drive, break down tent, collect banners/signs etc.

- Third Shift Volunteers meet truck at warehouse to help unload truck (professionals will move the big stuff)

POST-DRIVE

- Assist with thank-you letters and follow-up publicity, share photos etc.

Again, thank you for considering sponsoring a Furniture Drive.  For more information about us, please visit our website at www.furnituresharehouse.org.  We would also be very happy to give your volunteers a tour of our warehouse before the Drive so they can see first-hand what we do and how we do it and feel great about helping to collect furniture for Westchester families in need!

For more information, contact:

Kate Bialo

Executive Director

Furniture Sharehouse

Westchester’s Furniture Bank

www.furnituresharehouse.org

Cell 914.661.7259

bialok@aol.com

(October 2024)